## Summary
PAWJAI Change Log & Fix Schedule | PAWJAI Change Log & Fix Schedule | PAWJAI Change Log & Fix Schedule | PAWJAI Change Log & Fix Schedule | PAWJAI Change Log & Fix Schedule | PAWJAI Change Log & Fix Schedule | PAWJAI Change Log & Fix Schedule | PAWJAI Change Log & Fix Schedule
Generated 2026-07-02. Tracks completed security/backend work, remaining risks, and the next implementation schedule.
Metric | Value | Notes |  | Status Mix | Count | Priority Mix | Count
Completed changes logged | 13 | Rows in Change Log marked Done |  | Done | 0 | P0 | 3
Scheduled/manual tasks | 12 | Rows in Schedule |  | In Progress | 0 | P1 | 5
Open risks | 5 | Rows in Open Risks |  | Scheduled | 8 | P2 | 4
Last full verification | 2026-07-02 | npm run verify passed: typecheck, 68 tests, lint 0 errors, high audit gate |  | Manual | 3 | P3 | 0
Known lint warnings | 20 | next/no-img-element warnings only |  | Blocked | 0
Known dependency advisory | Moderate | PostCSS via Next; do not force-fix downgrade |  | Watch | 1
Today’s answer
The core vulnerable admin gate work is complete and verified. The remaining work is setup and hardening: enable leaked-password protection, create real admin accounts, reconcile Supabase migration history, tune remaining advisor warnings, convert key images to next/image, and commit/deploy in clean chunks.

## Change Log
Completed Changes | Completed Changes | Completed Changes | Completed Changes | Completed Changes | Completed Changes | Completed Changes | Completed Changes
What has already been changed or fixed in the PAWJAI system.
Area | Change/Fix | Details | Status | Priority | Owner | Date | Files / Notes
Security | Replaced passphrase admin gate | Moved admin access from passphrase/cookie to Supabase Auth role checks. | Done | P0 | Codex | 2026-06-15 | utils/admin-auth.ts, app/admin/login/page.tsx
Security | Added role model | Added admin, shelter_admin, and adopter role support through profiles and shelter_users. | Done | P0 | Codex | 2026-06-15 | types/database.ts, utils/admin-authorization.ts
Security | Scoped shelter admins | Shelter admins can manage only linked shelter records; global admins keep full workspace access. | Done | P0 | Codex | 2026-06-15 | app/admin/bookings, app/admin/dogs
Admin UX | Redesigned admin login | Created a shared admin/shelter login screen with email and password fields. | Done | P1 | Codex | 2026-06-15 | app/admin/login/page.tsx
Admin UX | Added account management | Global admins can create/revoke global and shelter admin accounts from the admin UI. | Done | P1 | Codex | 2026-06-15 | app/admin/accounts
Security | Added audit logging | Admin actions now write audit events; admins can review /admin/audit. | Done | P1 | Codex | 2026-06-15 | utils/admin-audit.ts, app/admin/audit
Security | Added DB-backed rate limiting | Rate limits added to auth, admin login, bookings, documents, donations, and appointment messages. | Done | P1 | Codex | 2026-06-15 | utils/rate-limit.ts
Backend | Applied targeted Supabase migrations | Created audit events, rate-limit buckets, booking guard index, and advisor security fixes. | Done | P0 | Codex | 2026-06-15 | supabase/migrations/2026061512*.sql
Security | Reduced Supabase advisor issues | Set function search_path and removed broad public storage listing policies. | Done | P1 | Codex | 2026-06-15 | 20260615124500_supabase_advisor_security_fixes.sql
Agent System | Added agent map and playbooks | Added stable docs for future Codex/Claude work to reduce context and token waste. | Done | P2 | Codex | 2026-06-15 | docs/agent-map.md, docs/playbooks
Cleanup | Removed duplicate files | Deleted stale duplicate page/test/client files and corrupt build artifacts. | Done | P2 | Codex | 2026-06-15 | app/messages/page 2.tsx, duplicate tests/utils
Next.js | Moved middleware to proxy | Replaced deprecated middleware.ts with proxy.ts for Next 16 compatibility. | Done | P1 | Codex | 2026-06-15 | proxy.ts
Verification | Added verify workflow | Repo now has one command for typecheck, tests, lint, and high-severity audit. | Done | P1 | Codex | 2026-06-15 | package.json

## Schedule
Next-Step Schedule | Next-Step Schedule | Next-Step Schedule | Next-Step Schedule | Next-Step Schedule | Next-Step Schedule | Next-Step Schedule | Next-Step Schedule | Next-Step Schedule | Next-Step Schedule
Use this tab as the active checklist. Update Status and Actual Status as work moves.
Step | Task | Description | Status | Priority | Owner | Start | Target | Notes / Dependencies | Actual Status
1 | Enable leaked password protection | Turn on leaked password protection in Supabase Auth dashboard. | Manual | P0 | Supabase Dashboard | 2026-07-02 | 2026-07-02 | Required dashboard setting; code cannot safely toggle it here. | Not Started
2 | Create first global admin | Create/confirm one real PawJai global admin account, then retire passphrase habit entirely. | Manual | P0 | Sudlabha | 2026-07-02 | 2026-07-03 | Needed before using /admin/accounts smoothly. | Not Started
3 | Create shared shelter admins | Use /admin/accounts to create one shared shelter_admin account per shelter. | Manual | P0 | Sudlabha | 2026-07-03 | 2026-07-05 | Use strong passwords and rotate when staff changes. | Not Started
4 | Review admin flows with real data | Log in as global admin and shelter admin; verify dogs, bookings, audit, accounts, ads permissions. | Scheduled | P1 | Codex | 2026-07-05 | 2026-07-06 | Requires valid admin credentials. | Not Started
5 | Reconcile Supabase migration history | Fix remote/local migration drift so future supabase db push is safe again. | Scheduled | P1 | Future Pass | 2026-07-06 | 2026-07-08 | Do carefully; avoid replaying old migrations against live schema. | Not Started
6 | Run Supabase advisors again | Capture current security/performance warnings after manual settings and migrations. | Scheduled | P1 | Codex | 2026-07-08 | 2026-07-08 | Use advisors output as source of truth. | Not Started
7 | Tune RLS performance warnings | Replace repeated auth calls in policies with initplan-friendly patterns where advisor recommends. | Scheduled | P2 | Future Pass | 2026-07-09 | 2026-07-11 | Backend performance hardening; not a launch blocker. | Not Started
8 | Clean duplicate index warning | Inspect and drop safe duplicate index reported by Supabase advisors. | Scheduled | P2 | Future Pass | 2026-07-11 | 2026-07-11 | Verify index names and usage before dropping. | Not Started
9 | Convert key img tags to next/image | Address the 20 lint warnings by converting highest-traffic images first. | Scheduled | P2 | Codex | 2026-07-12 | 2026-07-13 | Performance polish; verify responsive sizing visually. | Not Started
10 | Watch moderate Next/PostCSS advisory | Track Next release path; avoid npm audit fix --force because it suggests unsafe downgrade. | Watch | P2 | Future Pass | 2026-07-14 | 2026-07-14 | Recheck after Next update. | Watching
11 | Commit changes in chunks | Review dirty worktree and commit admin/security/docs changes separately from newer UX work. | Scheduled | P1 | Sudlabha | 2026-07-02 | 2026-07-04 | Important before deployment or handoff. | Not Started
12 | Deployment smoke test | After account setup and commits, run production build/deploy smoke checks on admin and user routes. | Scheduled | P1 | Codex | 2026-07-14 | 2026-07-15 | Use real environment variables and route checks. | Not Started

## Open Risks
Open Risks & Watch Items | Open Risks & Watch Items | Open Risks & Watch Items | Open Risks & Watch Items | Open Risks & Watch Items | Open Risks & Watch Items
Remaining vulnerabilities, operational risks, and what to do about them.
Risk | Why It Matters | Severity | Mitigation | Status | Owner
Supabase migration drift | Remote migration history does not match local migrations; db push could replay old SQL. | High | Use targeted SQL until reconciled; schedule migration-history cleanup. | Scheduled | Future Pass
Dashboard-only security setting | Leaked password protection still needs manual enabling. | High | Enable in Supabase Auth dashboard. | Manual | Supabase Dashboard
Shared shelter accounts | Shared credentials reduce per-person traceability. | Medium | Use one account per shelter only if needed; rotate password when staff changes; audit events still log account-level actions. | Manual | Sudlabha
Moderate dependency advisory | Next currently pulls a vulnerable PostCSS range according to npm audit. | Medium | Do not force downgrade; watch patched Next release path. | Watch | Future Pass
Image performance warnings | 20 img warnings remain; not failing verification but can affect LCP/bandwidth. | Low | Convert priority pages to next/image. | Scheduled | Codex